PROJECT HUITZILINREFLEX

Week 3 — Perception Pipeline Deep-Dive Playbook

Every task, in order, to get from a working patrol loop to a detection node that flags incoming projectiles in simulated and recorded depth — at ≥95% with a quantified false-positive rate.

What this playbook is

This zooms all the way in on Week 3 (Perception Pipeline on Synthetic & Recorded Depth) — the first week the camera matters. It is built as a checklist of numbered tasks, and then each task is expanded into a card with an objective, concrete steps, acceptance criteria, search keywords, and the traps to avoid. Work top to bottom; check boxes as you go. It inherits the Week 2 patrol stack and stays pure simulation — no real OAK-D (Week 6) and no Kalman/dodge (Week 4) yet.

| Phase | Covers | Tasks | Ends when |
| --- | --- | --- | --- |
| Week 3 — Perception Pipeline | Sim depth sensor, thrown-object scenarios, detection node, labeled rosbag regression | W3-01 → W3-22 | The detection node flags ≥95% of simulated incoming clusters with a quantified false-positive rate |

# How to Use This Playbook

Task IDs and order

Tasks are numbered W3-01…W3-22. The order is deliberate — later tasks assume earlier ones are done. Each task is small enough to finish in one sitting, and the cards are grouped into the six work areas of the week.

Anatomy of a task card

Objective: the one outcome the task produces.

Why it matters: the reason it’s in the plan (skip-at-your-peril context).

Steps: the checkable sub-tasks that fill the card out.

Done when: acceptance criteria. Don’t check the box until these pass.

Search: keywords to paste into docs / forums when you’re stuck.

Watch-out: the specific trap that catches builders here.

Conventions

- ☐ boxes are yours to tick. In Word, click into the box to mark progress, or print and check by hand.

- Commands shown are representative and stable; for anything version-sensitive, follow the official docs. The stack is pinned to ROS 2 Jazzy · Gazebo Harmonic · ArduPilot SITL · pymavlink on Ubuntu 24.04 (see the project CLAUDE.md / SETUP.md).

- Commit early and often, and update the contract docs in the same commit as the code — several acceptance criteria depend on architecture.md / frames.md staying true.

# Where We Are — Scope, Inheritance & Environment

1. The bright line

Week 3 of 9, Phase A (Foundations & Simulation). Everything this week is pure simulation — synthetic and recorded depth only. No real OAK-D hardware (that is Week 6), and no predictive Kalman filter or dodge command (that is Week 4). If a task tempts you toward predicting an intercept or commanding a maneuver, it’s misfiled — Week 3 only has to see the threat.

Week 3 Definition of Done: the detection node flags ≥ 95% of simulated incoming clusters, with a quantified false-positive rate, scored repeatably against a labeled rosbag library — demonstrated on a fresh checkout.

2. What Week 3 inherits (from the Week 2 handoff)

- A working autonomous patrol loop in SITL via `ros2 launch huitzilin_sim week2_sitl.launch.py` (43 laps, mean 29.51 s, stdev 0.93 s).

- A stable bridge with the `/huitzilin/odom`, `/huitzilin/state`, `/huitzilin/cmd_vel` contracts and a single NED↔ENU conversion point.

- Rosbag + CSV telemetry tooling, ready for labeled scenario capture.

- A Gazebo model to hang the depth sensor on (`iris_with_standoffs`; Pass-B fidelity deferred to Week 7–8).

- Already-drafted provisional contracts for `/oak/points`, `/oak/depth` (Wk3) and `/threat/centroid` (Wk4) in architecture.md — this week makes the Wk3 ones real.

- Open from Week 2: W2-05 Pass-B model, W2-18 fresh-checkout sign-off (closed in W3-02).

3. Environment reality — read before W3-04

This is the single fact that shapes Week 3. A simulated depth camera is a GPU-rendered sensor. The primary dev box is WSL2 on Windows with an Intel Iris Xe GPU, which has no GPU passthrough — Gazebo already runs headless at ~24% real-time there, and it cannot render depth frames at anything near 30 fps.

- Render depth on the native box. Do all sensor-rendering and scenario-capture work on the native-Ubuntu Dell Inspiron 3670 (i5-8400 / Intel UHD630), which has a real GPU. Keep SITL/flight logic on either box; isolate the depth render where the GPU is.

- Judge timing in sim time, not on a wristwatch. Keep `use_sim_time` consistent across the graph and drive every rate/latency check off `/clock` and message stamps. A frame-rate or recall-timing gate measured in wall-clock will look ~4× wrong on the WSL2 box.

- Capture once, replay forever. Because live depth is expensive on this hardware, the labeled rosbag library (W3-10) is not a nicety — it is how detection development becomes fast, offline, and deterministic.

# The Master Checklist

The full list of what needs to happen, in order. This page is your at-a-glance progress tracker; each row expands into a detailed task card later in this document.

Inherited State & Setup

| ☐ | ID | Task |
| --- | --- | --- |
| ☐ | W3-01 | Verify the Week 2 baseline still flies (regression gate) |
| ☐ | W3-02 | Close out the Week 2 carry-overs |
| ☐ | W3-03 | Scaffold the perception package |

Simulated Depth Sensor (Gazebo)

| ☐ | ID | Task |
| --- | --- | --- |
| ☐ | W3-04 | Add a simulated depth/stereo camera to the Gazebo model |
| ☐ | W3-05 | Bridge depth + point cloud into ROS 2 |
| ☐ | W3-06 | Publish the camera TF (static transforms) |
| ☐ | W3-07 | Verify the depth stream in RViz |

Synthetic Threat Scenarios

| ☐ | ID | Task |
| --- | --- | --- |
| ☐ | W3-08 | Build the thrown-object (projectile) spawner |
| ☐ | W3-09 | Define the scenario matrix (with ground-truth labels) |
| ☐ | W3-10 | Capture the labeled rosbag library |

Detection Node

| ☐ | ID | Task |
| --- | --- | --- |
| ☐ | W3-11 | Detection node skeleton |
| ☐ | W3-12 | Spatial slice & noise filter (ROI) |
| ☐ | W3-13 | Differential clustering (find the moving cluster) |
| ☐ | W3-14 | Centroid extraction & publishing |
| ☐ | W3-15 | Tune detection thresholds |

Rosbag Library & Regression

| ☐ | ID | Task |
| --- | --- | --- |
| ☐ | W3-16 | Build the offline regression harness |
| ☐ | W3-17 | Quantify detection rate & false-positive rate |
| ☐ | W3-18 | Regression-proof the library |

Integration, Reproducibility & Definition of Done

| ☐ | ID | Task |
| --- | --- | --- |
| ☐ | W3-19 | Update contracts & docs |
| ☐ | W3-20 | Reproducible bring-up (launch + SETUP) |
| ☐ | W3-21 | End-to-end Week 3 acceptance run (recorded) |
| ☐ | W3-22 | Week 3 retro, journal & Week 4 handoff |

# Week 3 — Task Cards

Goal: stand up a simulated OAK-D-class depth sensor, generate and record labeled thrown-object scenarios, and build a detection node that flags incoming clusters at ≥95% with a quantified false-positive rate — all reproducible from a fresh checkout.

Inherited State & Setup

W3-01  —  Verify the Week 2 baseline still flies (regression gate)	1–2 hrs

Objective: Confirm the inherited patrol stack launches and flies a clean lap before any perception code is added.

Why it matters: Week 3 stacks on top of a working bridge + patrol. A silent Week 2 regression now will masquerade as a perception bug for hours later.

Steps

☐  From a fresh shell, source the stack, launch SITL + Gazebo (iris_runway), then `ros2 launch huitzilin_sim week2_sitl.launch.py`.

☐  Arm → takeoff → `/huitzilin/start_patrol`; confirm a clean lap with telemetry CSV + rosbag written.

☐  Confirm `sitl_frame.parm` still loads (FRAME_CLASS=1) and SITL fans out to both 14552 (bridge) and 14553 (patrol).

Done when

- A closed patrol lap flies and logs, matching the Week 2 evidence (mean lap ~29.5 s).

Search: ros2 launch huitzilin_sim week2_sitl, ardupilot_gz iris_runway, colcon build symlink-install

Watch-out: Run from a brand-new shell. Hidden env left over from last week’s session is what makes “it worked before” a lie.

W3-02  —  Close out the Week 2 carry-overs	1 hr

Objective: Clear W2-18 (teammate fresh-checkout sign-off) and consciously park W2-05 (Pass-B model fidelity).

Why it matters: An unsigned reproducibility gate and an undecided model both turn into Week 3 blockers the moment a teammate — or the depth sensor — needs them.

Steps

☐  Get the W2-18 fresh-checkout sign-off recorded in `JOURNAL.md`, or log the remaining gap explicitly.

☐  Re-affirm the decision to keep W2-05 deferred: hang the depth sensor on the stock `iris_with_standoffs` model; real mass/inertia/motor tune stays in Week 7–8.

☐  Note any contract drift since Week 2 in `architecture.md` before adding new perception topics.

Done when

- W2-18 is signed off (or its gap logged) and the “depth-on-stock-model” decision is written down.

Search: reproducibility sign-off, ardupilot_gazebo iris model, deferred work tracking

Watch-out: Don’t quietly re-open W2-05 to “make depth nicer.” A half-tuned airframe now just adds a variable to every perception test — Pass-B is a Week 7–8 job.

W3-03  —  Scaffold the perception package	2 hrs

Objective: A place for Week 3 code to land — a `huitzilin_perception` ament_python package, built and committed empty.

Why it matters: Scaffolding first lets the sensor bring-up, the detector, and the regression harness develop in parallel without colliding with the flight stack.

Steps

☐  Decide: a sibling `huitzilin_perception` package (recommended) vs. new nodes inside `huitzilin_sim`. A sibling keeps perception deps out of the flight package.

☐  Declare deps: rclpy, sensor_msgs, geometry_msgs, visualization_msgs, tf2_ros, ros_gz_image/ros_gz_bridge, numpy; optional open3d/python3-pcl for clustering.

☐  Register entry points AND `data_files` (launch/params/config) in `setup.py` — forgetting `data_files` is why launch/param files “vanish” after install (Week 2 lesson).

☐  `colcon build --symlink-install` from the repo root; commit the empty scaffold.

Done when

- The package builds clean and its empty nodes are importable / runnable.

Search: ros2 pkg create ament_python, setup.py data_files launch, ros_gz_image bridge dependency

Watch-out: Keep depth processing OUT of `mav_bridge`. Perception is its own node graph; the only seam to flight is the Week 4 `/cmd/evade` path.

Simulated Depth Sensor (Gazebo)

W3-04  —  Add a simulated depth/stereo camera to the Gazebo model	half day

Objective: An OAK-D Lite-like depth sensor rigidly mounted on the drone in Gazebo, publishing depth + point cloud in sim.

Why it matters: Synthetic depth is the entire input to Week 3. Modeling the real sensor’s resolution/FOV/rate now means the detector you tune actually transfers to the real OAK-D in Week 6.

Steps

☐  Add a `<sensor>` (depth_camera / rgbd_camera) to the drone SDF at the `camera_link` mount offset.

☐  Match OAK-D Lite specs: ~640×480 depth, ~73° DFOV, 30 fps target, ~0.2–19 m range; clip min/max to the real working band.

☐  Add Gaussian sensor noise so the detector isn’t tuned against impossibly clean depth.

☐  Set the sensor’s output frame to `camera_optical_frame` (Z-forward optical convention).

Done when

- `gz topic -l` shows the depth + points topics and the frames render in the Gazebo image viewer.

Search: gazebo depth_camera sensor SDF, gz sim rgbd_camera, OAK-D Lite FOV resolution range, gazebo camera noise model

Watch-out: GPU-rendered sensors are THE catch on this project’s hardware (see Environment, §3). The WSL2 / Iris Xe box cannot render depth at rate — do all sensor-rendering work on the native-Ubuntu box.

W3-05  —  Bridge depth + point cloud into ROS 2	2–3 hrs

Objective: `/oak/depth` (sensor_msgs/Image) and `/oak/points` (sensor_msgs/PointCloud2) visible in ROS 2, on the contracts already drafted in `architecture.md`.

Why it matters: The detector is a ROS node; it needs Gazebo’s depth to cross the bridge with the right type, QoS, and frame.

Steps

☐  Configure `ros_gz_image` / `ros_gz_bridge` for the depth image, `camera_info`, and point-cloud topics.

☐  Use the provisional contracts: best-effort, keep-last 1, frame `camera_optical_frame`.

☐  Keep `use_sim_time` consistent across the whole graph (Week 2 lesson — stamps must agree or the Week 4 Kalman breaks).

☐  Confirm with `ros2 topic hz /oak/points`, judged in sim time.

Done when

- Depth + points echo in ROS 2 with the correct type/QoS and a sane sim-time rate.

Search: ros_gz_image image_bridge, ros_gz_bridge PointCloud2, sensor data QoS best_effort, use_sim_time clock bridge

Watch-out: Reliable QoS on a point-cloud topic stalls the graph; best-effort + keep-last 1 is correct. A QoS mismatch shows up as “topic present, zero messages received.”

W3-06  —  Publish the camera TF (static transforms)	2 hrs

Objective: `base_link → camera_link → camera_optical_frame` published so depth points land in the body frame.

Why it matters: The threat centroid must live in `base_link` for the Week 4 dodge (“left” is a body concept). Without TF the points float in an unrelated frame.

Steps

☐  Add a static_transform_publisher for `base_link → camera_link` using the planned mount offset (exact value measured in Phase B).

☐  Add the standard optical rotation `camera_link → camera_optical_frame`.

☐  Verify in RViz: the cloud aligns under the body; `ros2 run tf2_tools view_frames` matches `docs/frames.md`.

Done when

- The TF tree matches `docs/frames.md` and the cloud renders correctly in `base_link`.

Search: tf2 static_transform_publisher, camera optical frame rotation, view_frames tf tree, REP-103

Watch-out: The optical-frame rotation is the classic sign-flip trap — get it wrong and every centroid is mirrored, which later looks exactly like a detection bug.

W3-07  —  Verify the depth stream in RViz	1–2 hrs

Objective: A confirmed, human-eyeballed depth + point-cloud stream you trust as ground input.

Why it matters: Every later metric is meaningless if the input is wrong. Confirm it once, visually, before building the detector on top of it.

Steps

☐  In RViz add PointCloud2 + Image displays on the `/oak` topics (set display QoS to best-effort).

☐  Fly a patrol lap; confirm world geometry (runway, ground plane) is stable and correctly placed.

☐  Note the achieved frame rate in sim time and any dropouts.

Done when

- A stable, correctly-framed depth stream is visible across a full patrol lap.

Search: rviz2 PointCloud2 display, rviz depth image, fixed frame rviz, ros2 topic hz sim time

Watch-out: If RViz shows nothing, check the Fixed Frame and the display QoS before suspecting the sensor — a QoS mismatch silently shows empty.

Synthetic Threat Scenarios

W3-08  —  Build the thrown-object (projectile) spawner	half day

Objective: A scripted way to spawn a projectile in Gazebo and launch it at the drone with a set velocity.

Why it matters: You can’t measure detection without repeatable incoming objects. The spawner is the source of every scenario and every label.

Steps

☐  Create a small projectile model (sphere/can-sized, with mass) and a spawn + impulse script (gz service / ros_gz).

☐  Parameterize launch speed, approach angle, object size, and miss-distance (closest approach).

☐  Make spawns deterministic (seeded) so a scenario replays identically.

Done when

- A single command spawns a projectile that flies a repeatable path at/past the drone.

Search: gz sim spawn entity service, gazebo apply impulse velocity, ros_gz spawn model, deterministic sim seeding

Watch-out: Spawn relative to the drone’s current pose, not world origin — a world-fixed spawn drifts out of frame as the drone patrols.

W3-09  —  Define the scenario matrix (with ground-truth labels)	half day

Objective: An enumerated set of scenarios spanning hits, near-misses, and clean negatives, each with a ground-truth label.

Why it matters: The DoD is a true-positive rate AND a quantified false-positive rate — both require labeled positives and negatives.

Steps

☐  Vary speed (slow→fast), angle (head-on, oblique), size (small→large), and miss-distance (direct hit → wide miss).

☐  Include negatives: no object; benign world motion; the drone’s own patrol motion only.

☐  Record the label per scenario (incoming / not-incoming, closest approach, time-to-closest).

Done when

- A scenario table with labels is committed, covering positives and negatives.

Search: test matrix design, ground truth labeling, true positive false positive definition, regression coverage

Watch-out: Under-weighting negatives inflates apparent accuracy — a detector that fires on everything scores 100% TP and is useless. Budget plenty of clean negatives.

W3-10  —  Capture the labeled rosbag library	half day

Objective: A versioned library of rosbags, one per scenario, holding depth + points + the label.

Why it matters: Replayable bags turn detection into an offline, deterministic regression you can re-run after every code change.

Steps

☐  For each scenario, record `/oak/depth`, `/oak/points`, `/clock`, `/huitzilin/odom`, and the projectile ground-truth pose to mcap.

☐  Name/label bags by scenario id; store a label sidecar (yaml/json) beside each bag.

☐  Keep large blobs out of git proper — track an index + checksums; store via LFS or an external path noted in SETUP.md.

Done when

- The bag library + label index is captured and re-playable.

Search: ros2 bag record mcap, rosbag2 storage mcap, ground truth pose logging, git lfs large files

Watch-out: Record `/clock` and set `use_sim_time` on replay, or every timestamp is wrong on playback and the detector’s timing logic misfires.

Detection Node

W3-11  —  Detection node skeleton	half day

Objective: A `detector` node subscribing to the depth/points contracts, with a clean, non-blocking processing tick.

Why it matters: A well-structured node is what makes Week 4’s Kalman + trigger a drop-in rather than a rewrite.

Steps

☐  Subscribe `/oak/points` (and/or `/oak/depth`) with best-effort QoS to match the publisher.

☐  Process on a timer/callback without blocking the executor (Week 1/2 lesson).

☐  Stub a `/threat/centroid` publisher (geometry_msgs/PointStamped, `base_link`).

Done when

- The node runs, receives frames, and publishes a (stub) centroid.

Search: rclpy PointCloud2 subscriber, sensor_msgs_py read_points, non-blocking executor timer, QoS matching

Watch-out: A reliable-QoS subscriber against a best-effort publisher receives nothing — match QoS first whenever “no messages” appears.

W3-12  —  Spatial slice & noise filter (ROI)	half day

Objective: A cleaned, down-sampled cloud limited to the region where a threat actually matters.

Why it matters: Clustering on a raw, full-range cloud is slow and noisy; gating to a working volume is what makes detection real-time and robust.

Steps

☐  Range-gate to the sensor’s reliable band (e.g. ~0.3–8 m) and crop to a frustum/ROI ahead of the drone.

☐  Voxel-downsample to a fixed leaf size for stable per-frame timing.

☐  Remove statistical outliers / NaNs from depth dropouts.

Done when

- The filtered cloud is stable, bounded, and an order of magnitude smaller than raw.

Search: pcl voxel grid downsample, passthrough filter range, statistical outlier removal, open3d voxel_down_sample

Watch-out: Don’t over-crop — a tight ROI that excludes fast oblique approaches misses exactly the threats you most need to catch.

W3-13  —  Differential clustering (find the moving cluster)	1 day

Objective: Isolate the incoming object as a cluster of sudden depth-value change between frames.

Why it matters: A projectile shows up as a drastic, localized depth differential; differencing against the recent background separates it from the static scene.

Steps

☐  Maintain a short rolling background (previous frame[s] / running model) and difference the current frame.

☐  Cluster the changed points (Euclidean clustering / connected components) into candidate objects.

☐  Reject clusters that match the static scene or the drone’s own egomotion (use `/huitzilin/odom`).

Done when

- An incoming object yields a single coherent cluster, distinct from the static world.

Search: euclidean cluster extraction pcl, frame differencing depth, background subtraction point cloud, egomotion compensation odom

Watch-out: The drone’s own motion induces apparent depth change everywhere — compensate with odom, or your “threat” is just the world sliding past.

W3-14  —  Centroid extraction & publishing	half day

Objective: The threat cluster reduced to a centroid (X, Y, Z) in `base_link`, published on `/threat/centroid`.

Why it matters: Week 4’s Kalman filter tracks the centroid over time; a clean, correctly-framed centroid is the contract between detection and prediction.

Steps

☐  Compute the cluster centroid; transform into `base_link` via TF.

☐  Publish geometry_msgs/PointStamped on `/threat/centroid` (reliable QoS) with the correct stamp.

☐  Publish a visualization marker so the centroid is visible in RViz.

Done when

- A stable centroid tracks the object and renders in RViz over the approach.

Search: point cloud centroid computation, tf2 transform PointStamped, geometry_msgs PointStamped publish, rviz marker

Watch-out: Stamp the centroid with the depth frame’s time, not “now” — a wall-clock stamp desynchronizes the Week 4 filter, especially at 0.24× sim.

W3-15  —  Tune detection thresholds	half day

Objective: Detection parameters (differential threshold, min cluster size, ROI, voxel size) tuned for high recall at low false-positive rate.

Why it matters: This is the dial the DoD’s 95% / FP numbers turn on; tuning it deliberately beats guessing.

Steps

☐  Expose every threshold as a ROS param (no magic numbers in code).

☐  Sweep thresholds against the bag library; chart TP vs FP (a small precision-recall / ROC sweep).

☐  Pick an operating point that hits ≥95% TP with a documented FP rate.

Done when

- A chosen parameter set is committed alongside the sweep that justifies it.

Search: precision recall tradeoff, ROC curve threshold sweep, ros2 parameter yaml, detection tuning

Watch-out: Don’t tune on the same bags you report on — hold out a test set, or your 95% is memorization, not detection.

Rosbag Library & Regression

W3-16  —  Build the offline regression harness	half day

Objective: A one-command script that replays the bag library through the detector and scores it.

Why it matters: A repeatable scorer turns “looks like it works” into a number you can defend and re-check on every commit.

Steps

☐  Replay each bag (`use_sim_time` on), run the detector, compare published threats to the labels.

☐  Count true/false positives/negatives per scenario; aggregate TP rate and FP rate.

☐  Emit a results table (and per-scenario pass/fail) to a file.

Done when

- The harness runs the whole library unattended and prints the metrics.

Search: rosbag2 play programmatic, ros2 bag play use_sim_time, detection evaluation script, confusion matrix python

Watch-out: Account for replay running faster/slower than real — drive scoring off message stamps, not wall-clock windows.

W3-17  —  Quantify detection rate & false-positive rate	2–3 hrs

Objective: The headline numbers — true-positive (recall) ≥ 95% and a stated false-positive rate — across the held-out scenarios.

Why it matters: This IS the Week 3 Definition of Done; everything else is in service of these two numbers.

Steps

☐  Run the harness on the held-out set; compute recall and FP rate (e.g. false positives per minute, or per negative scenario).

☐  Break results down by speed/angle/size to expose weak regimes.

☐  Write the numbers + method into `docs/week3_detection_evidence.md`, mirroring the Week 2 evidence doc.

Done when

- ≥ 95% detection with a quantified FP rate is recorded together with its method.

Search: recall precision computation, false positive rate per hour, evaluation methodology writeup

Watch-out: Report the FP rate honestly and prominently — a high TP rate with an unreported FP rate is the classic way detection projects fool themselves.

W3-18  —  Regression-proof the library	2 hrs

Objective: The bag library + harness wired so a future change that hurts detection is caught automatically.

Why it matters: Week 4 will change the upstream stream and add the trigger; a regression net keeps perception from silently degrading.

Steps

☐  Add a `regress` script entry that runs the harness and fails on a metric drop below threshold.

☐  Document how to add a new labeled scenario to the library.

☐  Record the current numbers as the regression floor.

Done when

- A single command re-verifies the metrics and fails loudly on regression.

Search: regression test threshold gate, smoke test robotics, reproducible evaluation

Watch-out: A regression suite no one runs is decoration — wire it into the weekly habit, even if CI is manual on this project.

Integration, Reproducibility & Definition of Done

W3-19  —  Update contracts & docs	2 hrs

Objective: Architecture, frames, and requirements updated to promote the Week 3 perception path from provisional to active.

Why it matters: The docs are the contract; Week 4 builds against them, and a stale contract is how the evasion node gets wired wrong.

Steps

☐  In `architecture.md`, move camera_driver/detector + `/oak/*` and `/threat/centroid` from provisional to active (Wk3); keep `/cmd/evade`, `/payload/alarm` provisional.

☐  Confirm `frames.md` TF tree matches what you published; record the mount-offset assumption.

☐  Trace detection back to REQ-02 (detect projectile); note REQ-03/04 stay in Week 4.

Done when

- The contract docs reflect the as-built Week 3 perception graph.

Search: ros2 interface contract docs, architecture node graph update, requirements traceability matrix

Watch-out: Update the contracts in the SAME commit as the code — a doc/code split is what produced the Week 2 `src/src` and port-mismatch hunts.

W3-20  —  Reproducible bring-up (launch + SETUP)	half day

Objective: A `week3_perception.launch.py` and SETUP additions so a fresh checkout brings up sim + depth + detector.

Why it matters: Reproducibility is a standing DoD on this project; a teammate (or the native box) must reproduce detection from the docs alone.

Steps

☐  Launch file: sim + depth bridge + TF + detector (+ optional patrol) in one command.

☐  Add the new deps and the bag-library location/checksums to `SETUP.md`; pin versions.

☐  Note which machine renders depth (the native-Ubuntu box) vs. which runs SITL.

Done when

- One command brings up the perception stack on a fresh checkout.

Search: ros2 launch composition, rosdep new dependencies, reproducible setup doc, vcstool repos

Watch-out: The depth-rendering machine split is exactly the “tribal knowledge” that breaks a checkout — write down which box does what.

W3-21  —  End-to-end Week 3 acceptance run (recorded)	2–3 hrs

Objective: From a clean shell, fly a patrol lap, throw the scenario battery, and watch the detector flag incoming clusters — captured as evidence.

Why it matters: A recorded pass is the proof for the validation matrix and the raw material for the vlog.

Steps

☐  Bring up the stack; run the scenario battery (positives + negatives).

☐  Confirm `/threat/centroid` fires on incoming, stays quiet on negatives; capture RViz + a rosbag.

☐  Re-run the regression harness and screenshot the metrics.

Done when

- The DoD scenario passes and is recorded with its metrics.

Search: end to end demo capture, rosbag2 record evidence, screen capture robotics demo

Watch-out: Run it from a brand-new shell on the documented machine — not the dev session where you’ve been hand-setting paths and params.

W3-22  —  Week 3 retro, journal & Week 4 handoff	2–3 hrs

Objective: Capture what happened, the numbers, and tee up the evasion week.

Why it matters: Weekly capture is what makes the final build doc and post-mortem cheap — and the vlog is in the spec.

Steps

☐  Update `JOURNAL.md`: detection numbers, what worked / didn’t, exact versions, sim-time caveats.

☐  Record the Week 3 vlog: the depth pipeline + a detection clip.

☐  Write the Week 4 handoff: the `/threat/centroid` contract, the bag library, and open items (real-sensor gap, Pass-B model, the `/cmd/evade` seam).

Done when

- The journal is updated and the Week 4 handoff + vlog are drafted.

Search: engineering retrospective, weekly devlog, build documentation cadence

Watch-out: Write the open questions for Week 4 now (centroid stamp timing, egomotion compensation, miss-distance threshold) — they’re the seeds of the Kalman tuning.

# Appendix A — Week 3 Acceptance Matrix

Map each part of the Definition of Done to how you verify it and where the evidence lives. Fill the Status column as you go.

| DoD item | How verified | Evidence | Status |
| --- | --- | --- | --- |
| Sim depth sensor runs | Depth + points render in Gazebo / RViz at sane sim-time rate | screen recording; W3-04/07 | ☐ |
| Depth bridged to ROS 2 | /oak/depth + /oak/points echo with correct type/QoS/frame | ros2 topic info; W3-05 | ☐ |
| Camera TF correct | view_frames matches frames.md; cloud aligns in base_link | tf tree image; W3-06 | ☐ |
| Threat scenarios defined | Scenario matrix with ground-truth labels committed | scenario table; W3-09 | ☐ |
| Labeled rosbag library | One bag + label per scenario, re-playable | bag index + checksums; W3-10 | ☐ |
| Detector publishes centroid | /threat/centroid tracks an incoming object in RViz | recording; W3-14 | ☐ |
| ≥95% detection rate | Held-out scenarios scored by the harness | docs/week3_detection_evidence.md; W3-17 | ☐ |
| FP rate quantified | False-positive rate stated with method | same evidence doc; W3-17 | ☐ |
| Reproducible from fresh checkout | Stack brought up via one launch on documented machine | SETUP.md + run; W3-20/21 | ☐ |

# Appendix B — Command Quick-Reference

Representative, stable commands. Follow the official docs for anything version-sensitive.

Inherited flight stack

- Sim: ros2 launch ardupilot_gz_bringup iris_runway.launch.py

- Our stack: ros2 launch huitzilin_sim week2_sitl.launch.py

- Build: colcon build --symlink-install  then  source install/setup.bash

Depth sensor & bridge

- List Gazebo topics: gz topic -l

- Image bridge: ros2 run ros_gz_image image_bridge /oak/depth

- Param bridge (points): ros2 run ros_gz_bridge parameter_bridge /oak/points@sensor_msgs/msg/PointCloud2[gz.msgs.PointCloudPacked

- Rate (sim time): ros2 topic hz /oak/points

- Static TF: ros2 run tf2_ros static_transform_publisher … base_link camera_link

Scenarios, bags & scoring

- Record: ros2 bag record -s mcap /oak/depth /oak/points /clock /huitzilin/odom

- Replay: ros2 bag play <bag> --clock  (run nodes with use_sim_time:=true)

- View frames: ros2 run tf2_tools view_frames

Tools / docs

docs.ros.org/en/jazzy · gazebosim.org (sensors) · github.com/gazebosim/ros_gz · ArduPilot ROS2+Gazebo: ardupilot.org/dev/docs/ros2-gazebo.html

# Appendix C — Troubleshooting (Week 3)

| Symptom | Likely cause & fix |
| --- | --- |
| Depth renders at a crawl / no frames | GPU-rendered sensor on a box with no GPU passthrough (WSL2 / Iris Xe). Move sensor rendering to the native-Ubuntu box (UHD630). There is no GL-accel fix on WSL2. |
| Topic present, zero messages received | QoS mismatch. Sensor topics are best-effort / keep-last 1; a reliable subscriber gets nothing. Match QoS on both sides (and in the RViz display). |
| Point cloud floats / is mirrored | Missing or wrong camera TF. Publish base_link→camera_link→camera_optical_frame; the optical-frame rotation is the usual sign-flip culprit. |
| Everything looks like a moving threat | Egomotion not compensated. Difference against a motion-compensated background using /huitzilin/odom; the world slides past as the drone patrols. |
| Timestamps wrong on bag replay | /clock not recorded or use_sim_time off. Record /clock; replay with --clock; set use_sim_time on every node. |
| High detection rate but feels wrong | Too few negatives, or tuning on the report set. Add clean negatives; hold out a test set and report on it only. |
| Projectile drifts out of frame | Spawned at world origin. Spawn relative to the drone’s current pose; seed for determinism. |
| Frame-rate / latency gate “fails” ~4× | Measured in wall-clock on a 0.24× sim. Judge against /clock and message stamps, not a wristwatch. |

# Appendix D — Keyword Index (Week 3)

Pair any unfamiliar term with the relevant tool name when you search (e.g. “PointCloud2 ros_gz_bridge”, “euclidean cluster extraction pcl”).

| Term | Meaning here |
| --- | --- |
| depth_camera / rgbd sensor | The Gazebo GPU-rendered sensor that synthesizes OAK-D-like depth. |
| /oak/depth, /oak/points | The depth Image and PointCloud2 topics the detector consumes. |
| ros_gz_image / ros_gz_bridge | Bridges Gazebo image/point-cloud topics into ROS 2. |
| camera_optical_frame | Z-forward optical frame the depth data is expressed in (REP-103). |
| best-effort QoS | Lossy, low-latency delivery — correct for high-rate sensor streams. |
| voxel grid downsample | Reduces cloud density to a fixed leaf size for stable timing. |
| ROI / range gate | Cropping the cloud to the working volume where a threat matters. |
| frame differential | Per-frame depth change that reveals a fast-moving object. |
| egomotion compensation | Subtracting the drone’s own motion (via /odom) from apparent change. |
| Euclidean clustering | Grouping nearby changed points into a candidate object. |
| centroid | The (X,Y,Z) center of the threat cluster, published in base_link. |
| /threat/centroid | PointStamped contract from detection → (Week 4) prediction. |
| ground-truth label | The known incoming/not-incoming truth attached to each scenario. |
| true / false positive | Correct detections vs. false alarms — the DoD’s two numbers. |
| recall / precision | Fraction of threats caught vs. fraction of alarms that are real. |
| rosbag (mcap) | Recorded topic stream replayed for deterministic regression. |
| use_sim_time / /clock | Makes ROS use Gazebo / replay time so stamps agree. |
| regression harness | Script that replays the bag library and scores the detector. |

Project HuitzilinReflex — Week 3. Loiter like a hover; first, learn to see the dart coming.